## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during development and include a detailed description of every step. Explain what problems you encountered, why you made certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log. If external sources where used as reference, please mention them in the description
Subject | Amount of hours | Date | Description | Bonus
Setting up the project and testing database connection | 1 | 2024-01-15 | Went through the base skeleton and connected the database and tested it
Creating database and tables | 1 | 2024-01-16 | Created tables and made it 'not null' where necessary and connected foreign keys
create facility method in controller | 6 | 2024-01-18 | Created models for facility, location and tags. And made a method to put the data in the correct table
Read and read all facility methods | 4 | 2024-01-23 | made a method to search for 1 facility based on the id and another method to show all
Delete facility method | 1 | 2024-01-24 | made a simple method to delete a facility and its tags
Search facility method | 5 | 2024-01-24 | Made a method to search for facilities based on name, city or tags. And any combination of those
Refactoring Query Logic to Model Methods | 4 | 2024-01-30 | Refactored query logic from controller to model methods for for improved code organization
Make two methods in controller | 1 | 2024-01-30 | Implemented two methods, "respondWithJson" and "handleError," to eliminate code redundancy and ensure consistent handling of responses throughout the application.
Make 5 queries run at once in update method | 1 | 2024-01-31 | Enhanced code efficiency by combining five separate queries into a single operation for more effective location data updates.
Delete method also deletes unused tags | 2 | 2024-01-31 | Modified the delete method to automatically remove tags associated with a deleted facility if they are not in use elsewhere.
Added PHPDoc for each function | 2 | 2024-01-01 | Enhanced code documentation by adding PHPDoc comments for each function, providing clear and structured information about their purpose, parameters, and return values.
Total amount of hours | 28